## Sheet1
ID | Risk | Probability 0 (Not Probable) 5 (Highly Probable) | Impact 0 (Low Impact) 5 (High Impact) | Priority | Migitation Response
1 | Financial Abuse | 3 | 4 | 7 | The BHR and TEM teams will ensure that data is only visible within the companies walls.
2 | Hiring unsuitable employees | 2 | 5 | 7 | Discuss with Dr. Jones to consider hiring a consultant to fix the issue. This will result in increased cost.
3 | Bringing in under qualified technicans | 2 | 5 | 7 | Discuss with Dr. Jones about considering on replacing the failing hardware. This will result in increased cost.
4 | Release of personal information | 2 | 3 | 5 | The development team will review the code to find any errors and correct them.
5 | Maliciously logging hours in TEM system | 3 | 4 | 7 | Require management to review employee hour sumbition before payment period is over.
6 | Ethics of employee don't match the company | 1 | 2 | 3 | Go over the companies values and encorporate them into everyday tasks.
7 | Employee requires compensation | 2 | 3 | 5 | Require employee to take safety quizzes. Also ensure employee retention rate is high to avoid paying unemployment benefits.
8 | TEM vendor leaks information | 1 | 2 | 3 | Go over the companies values and encorporate them into everyday tasks.
9 | Employees have low job satisfaction | 2 | 3 | 5 | Require employee to take safety quizzes. Also ensure employee retention rate is high to avoid paying unemployment benefits.
10 | Fraud | 3 | 4 | 7 | Monitor data closely and encrypt the information.
11 | Shortage of critical skillsets for employees | 2 | 4 | 6 | Offer quartly reviews for employees.
12 | Not following compliance regulatories | 2 | 3 | 5 | Require dual authentication froms end users for the BHR and TEM systems
13 | Shortage of skills in external labor force | 4 | 5 | 9 | Hire contractos for the BHR or TEM teams as needed. Also check if all employees are contributing to the team.
14 | Legacy systems in NCWG fail | 2 | 5 | 7 | Send an email to the employee that they are nearing the required date. Conduct an employee review if task does not get done.
15 | Lack of communication with BHR team and TEM teams | 1 | 3 | 4 | Have backup systems that will run when legacy systems fail.
16 | Restricted access to the BHR system | 3 | 4 | 7 | Discuss with Dr. Jones to consider setting up more routers in the company will increase costs.
17 | BHR or TEM systems go offline (network loss) | 2 | 2 | 4 | Address the issue with BHR and TEM teams to get replacement parts. Cost will not increase due to this being a vendor issue.
19 | Nature disaster destroys database | 4 | 4 | 8 | Dispatch utility trucks containing backup devices to bring back data into the company. Time and cost will range based on distance of disaster.
20 | Lack of funding for TEM and BHR to keep running | 1 | 4 | 5 | Bring up the issue with the stakeholders and address that funding is not sufficent enough to complete the project.